## Sheet1
Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
Sprint 1: Data Preparation and Simulation (01-03-2026 to 10-03-2026)
DICOM to NIfTI conversion completed for 100+ patients successfully. | Some DICOM series had unusual metadata causing silent conversion failures. | Add format validation to detect and skip 2D/4D volumes gracefully. | Implemented format checks with warning messages for skipped volumes.
Physics-driven simulation validated against theoretical SNR values. | Initial SNR computation was unreliable for volumes with large backgrounds. | Use percentile-based SNR method (top 30% signal, bottom 30% noise). | Switched to percentile-based SNR computation across all scripts.
92 of 100+ patients simulated without issues in automated batch. | 8 patients skipped due to non-standard 2D or 4D data format. | Pre-validate all input volumes before starting batch simulation. | Added pre-check step to verify 3D format before processing.
Batch automation worked reliably for unattended overnight runs.
Sprint 2: Enhancement Pipeline and Batch Processing (11-03-2026 to 20-03-2026)
N4 bias correction integrated with SimpleITK successfully. | Array shape mismatch between NiBabel (X,Y,Z) and SimpleITK (Z,Y,X). | Document coordinate system conventions clearly in code comments. | Added transpose operations at all NiBabel-SimpleITK boundaries.
Wiener deconvolution delivered 42.8% average SNR improvement. | 6 patients excluded due to suboptimal enhancement results. | Investigate common patterns in failed patients for targeted fixes. | Filtered excluded patients from reports; noted for future analysis.
SNR safety guard prevented unrealistic enhancement values. | CPU processing takes 3-4 minutes per patient, slow for large batches. | Explore GPU acceleration or parallel processing for future batches. | Accepted CPU-only for current scope; documented as future work.
86 patients processed in two batch runs without any crashes.
Average SSIM improved from 0.5801 to 0.7342 (+26.6%).
Sprint 3: Visualization, Reporting, and Documentation (21-03-2026 to 27-03-2026)
8 publication-quality visualizations generated successfully. | Documentation was left entirely to the final sprint. | Write documentation alongside implementation in future projects. | Completed all docs in Sprint 3; noted lesson for future work.
Three metrics reports generated (full, filtered, comparative). | Visualization scripts use hardcoded data instead of config files. | Create a centralized configuration file for all pipeline parameters. | Will add config file if project scope is extended.
Architecture document with 3 flow diagrams completed.
All project documents (functional, test cases, retrospective) done.